## Sheet1
Project Information
Project Name: | Tenant Finder |  | Project Manager: | Wan Muhd Ismat
Date: | 17.10.2020 |  | Project Duration: | 14 Months
Task Name | Resource | Rate | Hours | Estimate
Requirement Analysis
Analysis functional & non-functional requirements | ismat | 100 | 168 | 16800
Analysis quality assurance requirements | akmal sabri | 100 | 200 | 20000
Analysis recognization of the risks | akmal khairi | 100 | 72 | 7200
Feasibility Study
Study software requirement specification | imran | 100 | 120 | 12000
Study economic aspect of the system | ismat | 100 | 48 | 4800
Study legal aspect of the system | ismat | 100 | 48 | 4800
Study operation feasibility of the system | akmal khairi | 100 | 48 | 4800
Study technical of the system | akmal khairi | 100 | 48 | 4800
Study schedule of the system | imran | 100 | 48 | 4800
Design
Design description, name and fucntional of each module | ismat | 100 | 168 | 16800
Design an outline about the functionality of every module | akmal sabri | 100 | 200 | 20000
Design input and outputs for every module | akmal sabri | 100 | 168 | 16800
Design detail interface relationship and dependencies between modules | imran | 100 | 168 | 16800
Design database tables identified with key elements, type & size | akmal khairi | 100 | 168 | 16800
Design complete architecture diagrams along with technology details | imran | 100 | 168 | 16800
Implementation
code each system units | ismat | 100 | 1440 | 144000
code each system modules | akmal khairi | 100 | 1440 | 144000
integrate system units and modules | imran | 100 | 1440 | 144000
Testing
Deploy system into testing environment | akmal sabri | 100 | 120 | 12000
Unit testing | akmal khairi | 100 | 120 | 12000
Integration testing | ismat | 100 | 168 | 16800
System testing | imran | 100 | 168 | 16800
User acceptance testing (UAT) | akmal sabri | 100 | 168 | 16800
Installation/Deployment
Deploy system into production environment | akmal sabri | 100 | 120 | 12000
Check for any deployment issues | ismat | 100 | 120 | 12000
Released system into live production | akmal sabri | 100 | 120 | 12000
Maintenance
Bug fixing | ismat | 100 | 120 | 12000
Upgrade system to newer version | imran | 100 | 120 | 12000
Enhancement on new features | akmal khairi | 100 | 100 | 10000
Task Subtotal |  |  |  | 760400
3rd Party Costs
Software fee |  | Price per Unit/Month | Quantity/Month | Total Price
Adobe Creative Cloud |  | 377 | 14 | 5278
Web hosting |  | 441.79 | 14 | 6185.06
Web domain |  | 20.23 | 14 | 283.22
Licensed Software (IDE) |  | 80.66 | 14 | 1129.24
Hardware fee
Wifi |  | 500 | 1 | 500
Printer |  | 515 | 1 | 515
Laptop |  | 2000 | 4 | 8000
Hardware maintenance |  | 100 | 14 | 1400
Utilities fee
Electricity |  | 450 | 14 | 6300
Water |  | 35 | 14 | 490
Utilities maintenance |  | 150 | 14 | 2100
Support & Training fee
Training cost |  | 200 | 14 | 2800
Travel cost |  | 350 | 14 | 4900
Software maintenance & support charges |  | 2000 | 14 | 28000
Insurance |  | 800 | 14 | 11200
3rd Part Costs Subtotal |  |  |  | 79080.52
Estimate Summary
Task Subtotal |  |  |  | 760400
3rd Part Costs Subtotal |  |  |  | 79080.52
Estimate Total |  |  |  | 839480.52
Net Profit
Year | Cash Flow (RM) |  |  |  | Person | Salary
0 | -839480.52 |  |  |  | akmal khairi | 199600
1 | 167896.1 |  |  |  | ismat | 228000
2 | 167896.1 |  |  |  | imran | 223200
3 | 167896.1 |  |  |  | akmal sabri | 109600
4 | 167896.1
5 | 200000
Net Profit | 32103.88 | -167896.12
Payback Period
Year 5 | 200000 | -167896.12
Month 1 | 16666.6667 | -151229.4533
Month 2 | 16666.6667 | -134562.7867
Month 3 | 16666.6667 | -117896.12
Month 4 | 16666.6667 | -101229.4533
Month 5 | 16666.6667 | -84562.7867
Month 6 | 16666.6667 | -67896.12
Month 7 | 16666.6667 | -51229.4533
Month 8 | 16666.6667 | -34562.7867
Month 9 | 16666.6667 | -17896.12
Month 10 | 16666.6667 | -1229.4533
Month 11 | 16666.6667 | 15437.2133 | Break Even
Month 12 | 16666.6667 | 32103.88 | Net Profit
Return On Investment
Total cash Flow | 871584.4 | 1711064.92
Average | 6420.776
ROI | 0.76485